## Slide 1: RECIPE5ND VISION, SCOPE, AND PROJECT PLAN
TEAM MEMBERS: OGHENEOVO (Nova) Abu
Manuel Berlanga
Ethan Hann
Thu Le
Mark Odom

## Slide 2: PROJECT BACKGROUND
To create a recipe application for the Android line of smartphones
To create an application that will allow users to find potential meals using ingredients already available to them
STAKEHOLDERS
The only stakeholders for this project are our team members:
  Ogheneovo (Nova) Abu
  Manuel Berlanga
  Ethan Hann
  Thu Le
  Mark Odom

## Slide 3: USERS
Anyone with an Android smartphone who has an interest in finding recipes using ingredients already in their possession
Anyone who cooks at home
RISKS
The API (TheMealDB) becomes unavailable.
Lack of communication between team members
Members of the team become sick during the course of the project
Members’ computers stop working (BSOD, un-bootable, etc.)

## Slide 4: VISION STATEMENT
To provide a cost effective tool for everyday cooks to plan meals
LIST OF FEATURES
Search recipes by ingredients – allow the lookup of recipes based on user’s ingredients
Shopping lists – allow the user to keep multiple shopping lists to track ingredients they may need
Favoriting recipes – allow the user to favorite their frequently used recipes for quick access
Ingredients list – allow the user to keep track of the ingredients they have

## Slide 5: FEATURES WILL NOT BE DEVELOPED
Custom analytics – track user history to display frequented ingredients and recipes from other users
Dietary requirements – allow the user to filter recipes based on any dietary restrictions
Substitutions – allow the user to view substitutes for various ingredients in the recipe
Social media integration – allow the user to share their favorite recipes via social media
Add recipes – allow the user to add their own recipes to the database

## Slide 6: STATEMENT OF WORK
Features (Modules):
  Search recipes by ingredients
  Favorite recipes
  Edit ingredients list
  Shopping list
  View favorites list
  View details about a specific favorite
Intermediate deliverables:
  Requirements specification – outlines use cases, functional and non-functional requirements
  Design specification – describes the inner workings of the system
  Test plans and test cases – how testing will be handled
  Bug reports – describing any bugs and steps to reproduce them that arise during testing
  Source code for each module – code produced to meet the requirements
  Final presentation – a final presentation showing off the work done

## Slide 7: EFFORT ESTIMATES
Work Product | Effort Estimate (weeks)
Requirements specification | 1
Design specification | 1
Test plans and test cases | 2
Bug reports | 0.5
Source code | 8.5
Final presentation | 1

## Slide 8: RESOURCE LIST
Resource | Availability
TheMealDB | 99.9%
Physical/Virtual Android device | 100%
Computers | 99.9%
Internet | 99.9%
Github | 99.9%
Discord | 99.9%

## Slide 9: WORK BREAKDOWN AND ESTIMATES
Task | Estimation (weeks) | Assigned Member
Requirements document | 2 | All team members
Design document | 1 | All team members
Search recipes by ingredients | 4 | Ethan Hann
Favorite recipes | 4 | Ethan Hann
Ingredients list | 4 | Mark Odom
Shopping list | 4 | Manuel Berlanga
View favorites list | 4 | Thu Le
View details about a specific favorite | 4 | Ogheneovo (Nova) Abu
Code integration | 1 | All team members
Testing and document | 2 | All team members test their own modules Mark Odom does final QA testing
Debugging | 1 | All team members
Final Presentation | 1 | Thu Le

## Slide 10: RISK PLAN
Risk | Probability | Impact | Priority | Actions
Team member’s computer stop working | 3 | 5 | 15 | Team member will use a portable OS (Linux) that fits on USB drive. Team member will source a new computer. Team member will work on an open computer labs at UHCL.
Lack of communication | 4 | 3 | 12 | The team will prioritize communication over other tasks to ensure everyone is back on track.
Team member gets sick | 2 | 5 | 10 | Tasks will be rearranged to fill the team member’s role.
TheMealDB API goes offline and is unavailable | 1 | 4 | 4 | The research manager will find a new API that satisfies the needs in a timely manner